IMPLEMENTATION PLAN — PHASES AND DEPENDENCIES

This phase sequence follows the client's requested delivery schedule. No calendar dates or durations were supplied, so none are invented here.

PHASE 1 — DISCOVERY AND REQUIREMENTS

Activities: workshops with ATCO; confirm users, service model, routes, destinations, vessel capacity/payload, booking/threshold behavior, tariffs, policies, approval roles, payment/notification providers, reporting, data location, security, and acceptance authority.

Outputs: confirmed requirements, open-question answers, compliance matrix draft, scope boundaries, dependencies, risk register.

Gate: ATCO confirms requirements baseline and unresolved items are explicitly listed.

PHASE 2 — DESIGN CONCEPTS AND CLICKABLE PROTOTYPE

Activities: prepare two or three concepts; include requested navy/teal/white direction; design English and Arabic RTL; cover customer booking, corporate account, administration and boarding verification; recommended inclusion of material approval and booking status transitions.

Outputs: design concepts, selected direction, screen inventory, prototype link, accessibility and RTL review.

Gate: ATCO approves the prototype before development begins, as requested.

PHASE 3 — ARCHITECTURE AND TECHNICAL DESIGN

Activities: compare architecture options; confirm hosting/data location; define test and production environments; data model, role/access matrix, state machines, payment boundaries, audit events, backup/recovery, integrations.

Outputs: approved architecture, data model, integration plan, security plan, deployment approach.

Gate: ATCO IT/security and relevant stakeholders approve the technical baseline.

PHASE 4 — BUILD AND INTEGRATION

Workstreams: customer booking and ticketing; corporate accounts; agent flows; ATCO administration; operations/manifests/boarding; materials and charters; payment and finance; notifications; reports and exports; policy/versioning; audit logs; access controls.

Dependency: provider onboarding, API access, approved tariffs/policies, test credentials, content, and ATCO decisions must be available.

PHASE 5 — SYSTEM / SECURITY / INTEGRATION TESTING

Test: booking/payment and retry behavior; minimum thresholds; capacity; refunds; credit; agent settlements; material approval; QR/manual boarding; duplicate ticket use; permissions; notifications; exports; RTL/responsive behavior; backup/recovery; security findings.

Output: test evidence, defect list, retest records, release readiness report.

PHASE 6 — USER ACCEPTANCE TESTING

ATCO Operations, Finance and IT validate workflows against agreed acceptance criteria. Use approved test data; do not use real passenger/payment data unless explicitly approved.

Output: signed acceptance results, outstanding defects and agreed disposition.

Gate: named ATCO authority approves release.

PHASE 7 — PRODUCTION LAUNCH

Activities: configure production, confirm ATCO-owned accounts/domain/hosting/payment/messaging, run final backup and rollback checks, train staff, publish approved policies/tariffs, monitor launch.

Output: production release record, training completion, access/ownership register, support contacts.

PHASE 8 — INITIAL OPERATIONAL SUPPORT AND HANDOVER

Activities: monitor real operations, triage defects, support Operations/Finance/IT, deliver final manuals and technical documentation, repository/source code, deployment instructions, third-party licence inventory, and data export/handover.

Output: warranty/support start date, known issues, maintenance process, complete handover checklist.

ESTIMATION INPUTS REQUIRED BEFORE TIMELINE

- Number and availability of client decision-makers.

- Completeness of routes, fares, policies, operational limits and approval rules.

- Payment gateway selection/onboarding and test environment access.

- Messaging provider selection, sender approval, templates and consent process.

- Data-location and hosting requirements.

- Target integrations and availability of documentation/API credentials.

- Scope of PWA versus separate native iOS/Android apps.

- Required security testing, assurance, warranty and support coverage.

- Review/approval turnaround time and acceptance resources.

Timeline template:

Phase | Estimated duration | Planned start | Planned finish | Owner | Dependencies | Exit criteria | Status

Populate only after discovery and delivery-team estimation. Do not promise a launch date based on the client brief alone.